## Product Backlog
EcoTrack — Product Backlog
Module: ITS 610204 / ITS 64604 — Principles of Software Engineering ¦ SDG 13: Climate Action ¦ Semester: February 2026
ID | User Story | Acceptance Criteria | Priority | Story Points | Sprint | Status | Assigned To | Category | Notes
US-01 | As a user, I want to register and log in so that my data is saved securely. | User can create account, login, and logout successfully. | High | 5 | 1 | Done | Member 1 | Authentication
US-02 | As a user, I want to input my daily transport data so that it contributes to my carbon calculation. | User can enter car km, transit km, and flight hours with vehicle type. | High | 8 | 1 | Done | Member 2 | Activity Input
US-03 | As a user, I want to input my daily energy usage so that electricity and gas are tracked. | User can enter kWh and select energy source type. | High | 5 | 1 | Done | Member 2 | Activity Input
US-04 | As a user, I want to input my food and diet details so that food emissions are calculated. | User can enter number of beef, chicken, vegetarian, and vegan meals. | High | 5 | 1 | Done | Member 3 | Activity Input
US-05 | As a user, I want to input my consumption data so that shopping emissions are tracked. | User can enter number of purchases, clothing items, and device usage hours. | Medium | 5 | 1 | Done | Member 3 | Activity Input
US-06 | As a user, I want to save my daily log so that all inputs are stored for calculation. | All input fields are saved when the user clicks Calculate. | High | 3 | 1 | Done | Member 1 | Data Management
US-07 | As a user, I want to edit or delete a previous entry so that I can correct mistakes. | User can modify or remove any saved log entry. | Medium | 3 | 1 | Done | Member 4 | Data Management
US-08 | As a user, I want the system to calculate my total carbon footprint so that I know my daily CO2 impact. | System computes transport, energy, food, and consumption CO2 and sums them correctly. | High | 8 | 1 | Done | Member 2 | Calculation | Core feature
US-09 | As a user, I want to view a breakdown of my footprint by category so that I know where my emissions come from. | Results page shows transport, energy, food, consumption values separately. | High | 5 | 2 | Done | Member 3 | Results
US-10 | As a user, I want to see my footprint status (Low/Medium/High) so that I understand my impact level. | Status tag updates colour based on total CO2 vs thresholds. | High | 3 | 2 | Done | Member 3 | Results
US-11 | As a user, I want to see a visual bar chart of my emissions so that I can compare categories easily. | Animated bar chart renders correctly for each category. | Medium | 5 | 2 | Done | Member 2 | Results
US-12 | As a user, I want to compare my footprint to the global average so that I understand my relative impact. | Global average reference line or label shown on results page. | Medium | 3 | 2 | Done | Member 4 | Results
US-13 | As a user, I want to view my weekly history log so that I can track progress over time. | History table shows all past entries with date, category values, and total. | High | 5 | 2 | Done | Member 1 | History
US-14 | As a user, I want to filter my history by date so that I can review specific periods. | User can filter history table by date range. | Low | 3 | 2 | Done | Member 4 | History | Nice to have
US-15 | As a user, I want to view eco tips so that I can learn how to reduce my carbon footprint. | Tips page displays at least 6 actionable tips with impact levels. | High | 5 | 2 | Done | Member 5 | Eco Tips
US-16 | As a user, I want to see personalised tips based on my highest emission category so that advice is relevant. | Tips are filtered/highlighted based on the users top emission category. | Medium | 5 | 2 | Done | Member 5 | Eco Tips
US-17 | As a user, I want to generate an emissions report so that I can share or review my data. | User can export or view a summary report of their footprint history. | Low | 3 | 2 | Done | Member 1 | Reporting | Nice to have
US-18 | As an admin, I want to manage emission factors so that CO2 calculations stay accurate. | Admin can update emission multipliers for each activity type. | Medium | 5 | 2 | Done | Member 2 | Admin
US-19 | As an admin, I want to add or update eco tips so that users receive current advice. | Admin can create, edit, and delete eco tips from the system. | Low | 3 | 2 | Done | Member 5 | Admin
US-20 | As an admin, I want to view all user reports so that I can monitor platform usage. | Admin dashboard shows summary of all user activity. | Low | 3 | 2 | Done | Member 1 | Admin | Future enhancement
TOTAL STORY POINTS

## Sprint 1 Backlog
EcoTrack — Sprint 1 Backlog (Week 2: Design & Early Prototype)
Sprint Goal: Complete system design, UML diagrams, UI wireframes, and build core input & calculation features
Task ID | Task Description | User Story | Assignee | Estimated Hrs | Actual Hrs | Status | Notes
T1-01 | Define project scope and choose SDG | US-01 | Member 1 | 2 | 2 | Done
T1-02 | Write product vision document | US-01 | Member 1 | 3 | 3 | Done
T1-03 | Create user stories and product backlog | US-01 | Member 5 | 4 | 5 | Done
T1-04 | Set up Trello board and GitHub repository | US-01 | Member 4 | 2 | 2 | Done
T1-05 | Design Use Case Diagram (UML) | US-08 | Member 2 | 4 | 5 | Done | Draw.io
T1-06 | Design Class Diagram (UML) | US-08 | Member 3 | 4 | 4 | Done | Draw.io
T1-07 | Create UI wireframes and mockups | US-09 | Member 5 | 3 | 3 | Done
T1-08 | Build transport input feature | US-02 | Member 2 | 4 | 5 | Done | HTML/CSS/JS
T1-09 | Build energy usage input feature | US-03 | Member 2 | 3 | 3 | Done
T1-10 | Build food and diet input feature | US-04 | Member 3 | 3 | 3 | Done
T1-11 | Build consumption input feature | US-05 | Member 3 | 3 | 3 | Done
T1-12 | Implement save daily log functionality | US-06 | Member 1 | 3 | 4 | Done
T1-13 | Sprint 1 Review and Retrospective | US-01 | All | 2 | 2 | Done
TOTALS

## Sprint 2 Backlog
EcoTrack — Sprint 2 Backlog (Week 3: Build & Test)
Sprint Goal: Complete remaining prototype features, perform user testing, fix bugs, and finalize documentation
Task ID | Task Description | User Story | Assignee | Estimated Hrs | Actual Hrs | Status | Notes
T2-01 | Implement carbon calculator logic | US-08 | Member 2 | 5 | 5 | Done | Core algorithm
T2-02 | Build results breakdown view | US-09 | Member 3 | 4 | 4 | Done
T2-03 | Build footprint status indicator | US-10 | Member 3 | 2 | 2 | Done | Low/Med/High
T2-04 | Build visual bar chart for results | US-11 | Member 2 | 3 | 4 | Done | JS animation
T2-05 | Add global average comparison | US-12 | Member 4 | 2 | 2 | Done
T2-06 | Build weekly history log feature | US-13 | Member 1 | 4 | 4 | Done
T2-07 | Add date filter for history | US-14 | Member 4 | 2 | 3 | Done
T2-08 | Build eco tips page | US-15 | Member 5 | 3 | 3 | Done
T2-09 | Implement personalised tips logic | US-16 | Member 5 | 3 | 3 | Done
T2-10 | Add report generation feature | US-17 | Member 1 | 2 | 2 | Done
T2-11 | Write test cases for all features | US-08 | Member 3 | 3 | 3 | Done
T2-12 | Perform user testing and collect feedback | US-08 | All | 3 | 3 | Done
T2-13 | Fix bugs identified in testing | US-08 | Member 2 | 3 | 3 | Done
T2-14 | Compile final report and prepare slides | US-01 | All | 6 | 6 | Done | Week 4
T2-15 | Sprint 2 Review and Retrospective | US-01 | All | 2 | 2 | Done
TOTALS